## Sheet1
Standard Pruches Order Follow Up
Project No | 1 | Project Name | PLAYA Resorts Project | Organization Code | PL1
PO Num | PR Num | PR Line Number | PO Status | Project | Next Approver | Action Date | Vendor | Supplier | Buyer | Currency | PO Line | Shipment | Creation Date | Approved Date | Po Comments | Store Code | Description | UOM | Unit Price | Qty | Payment | Amount | Task | Task | Need By Date | VAT | Promise | Qty | Qty. Received | Qty. Cancelled | Qty. Delivered | Qty. Open | Closure Status
|  |  |  | Name |  |  |  | Site | [12 empty] | Terms |  | No. | name |  |  | Date | Billed
1762 | 1524 | 7 | APPROVED | PLAYA Resorts Project |  |  | المروه للتجارة والتوريدات | PLAYA | Karim Awad Saied Awad, Mr. | EGP | 1 | 1 | 2022-08-03 | 2022-08-11 |  | P140010000015 | اسمنت اسود رتبة 42 | Ton | 1447.368 | 120 | 100% 30 Days | 173684.16 |  |  | 2022-05-09 | 24315.7824 |  | 120 | 120 | 0 | 120 | 0 | CLOSED
1763 | 1791 | 2 | APPROVED | PLAYA Resorts Project |  |  | مؤسسة تعمير ستيل للتجاره والتوريدات جميع انواع الحديد والصلب | PLAYA | Karim Awad Saied Awad, Mr. | EGP | 4 | 1 | 2022-08-04 | 2022-08-11 |  | P150040000021 | علبة حديد 5*5سم | Ton | 20175.43 | 5 | 100% in advance | 100877.15 |  |  | 2022-07-28 | 14122.801 |  | 0 | 0 | 0 | 0 | 5 | OPEN
1763 | 1791 | 1 | APPROVED | PLAYA Resorts Project |  |  | مؤسسة تعمير ستيل للتجاره والتوريدات جميع انواع الحديد والصلب | PLAYA | Karim Awad Saied Awad, Mr. | EGP | 3 | 1 | 2022-08-04 | 2022-08-11 |  | P150040000020 | زاويه حديد 5*5سم | Ton | 15701.75 | 5 | 100% in advance | 78508.75 |  |  | 2022-07-28 | 10991.225 |  | 0 | 0 | 0 | 0 | 5 | OPEN
1763 | 1791 | 3 | APPROVED | PLAYA Resorts Project |  |  | مؤسسة تعمير ستيل للتجاره والتوريدات جميع انواع الحديد والصلب | PLAYA | Karim Awad Saied Awad, Mr. | EGP | 1 | 1 | 2022-08-04 | 2022-08-11 |  | P150020000185 | علبة حديد 10سم * 10سم طول 6 متر | Kilogram | 20.175 | 5000 | 100% in advance | 100875 |  |  | 2022-07-28 | 14122.5 |  | 0 | 0 | 0 | 0 | 5000 | OPEN
1763 | 1791 | 4 | APPROVED | PLAYA Resorts Project |  |  | مؤسسة تعمير ستيل للتجاره والتوريدات جميع انواع الحديد والصلب | PLAYA | Karim Awad Saied Awad, Mr. | EGP | 2 | 1 | 2022-08-04 | 2022-08-11 |  | P150020000051 | صاج ايكون مقاس 1 * 6 * 0.4 مم | Kilogram | 26.22 | 5000 | 100% in advance | 131100 |  |  | 2022-07-28 | 18354 |  | 0 | 0 | 0 | 0 | 5000 | OPEN
1764 | 1635 | 2 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-06 | 2022-08-11 |  | P800040000027 | Orange router | Each | 1680.13 | 1 | Immediate | 1680.13 |  |  | 2022-06-07 | 0 |  | 1 | 1 | 0 | 1 | 0 | CLOSED
1765 | 1794 | 14 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 13 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000178 | Rubber gasket 3" | Each | 15.7895 | 6 | Immediate | 94.7368 |  |  | 2022-07-29 | 13.2632 |  | 6 | 6 | 0 | 6 | 0 | CLOSED
1765 | 1794 | 11 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 10 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000175 | UPVC ball valve 3" PN10 commer | Each | 1009.0175 | 1 | Immediate | 1009.0175 |  |  | 2022-07-29 | 141.2619 |  | 1 | 1 | 0 | 1 | 0 | CLOSED
1765 | 1794 | 2 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 3 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000166 | UPVC pipe PN 10 gray color 2" commer | Meter | 38.5965 | 6 | Immediate | 231.5789 |  |  | 2022-07-29 | 32.4211 |  | 6 | 6 | 0 | 6 | 0 | CLOSED
1765 | 1794 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000165 | UPVC pipe PN 10 gray color 3" commer | Meter | 78.9474 | 6 | Immediate | 473.6842 |  |  | 2022-07-29 | 66.3158 |  | 6 | 6 | 0 | 6 | 0 | CLOSED
1765 | 1794 | 12 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 11 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000176 | swing check valve thread type 2" - PN 10 commer | Each | 95.8158 | 1 | Immediate | 95.8158 |  |  | 2022-07-29 | 13.4143 |  | 1 | 1 | 0 | 1 | 0 | CLOSED
1765 | 1794 | 8 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 7 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000171 | UPVC - socket 2" PN 10 commer | Each | 13.0088 | 2 | Immediate | 26.0175 |  |  | 2022-07-29 | 3.6425 |  | 2 | 2 | 0 | 2 | 0 | CLOSED
1765 | 1794 | 9 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 8 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000172 | UPVC - socket 3" PN 10 commer | Each | 48.9912 | 2 | Immediate | 97.9825 |  |  | 2022-07-29 | 13.7176 |  | 2 | 2 | 0 | 2 | 0 | CLOSED
1765 | 1794 | 3 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000164 | UPVC flange with adaptor 3" | Set | 54.1754 | 3 | Immediate | 162.5263 |  |  | 2022-07-29 | 22.7537 |  | 3 | 3 | 0 | 3 | 0 | CLOSED
1765 | 1794 | 6 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 5 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000169 | UPVC elbow 90 dg -2" PN10 commer | Each | 22.1491 | 4 | Immediate | 88.5965 |  |  | 2022-07-29 | 12.4036 |  | 4 | 4 | 0 | 4 | 0 | CLOSED
1765 | 1794 | 13 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 12 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000177 | swing check valve thread type 3" PN commer | Each | 343.9825 | 1 | Immediate | 343.9825 |  |  | 2022-07-29 | 48.1576 |  | 1 | 1 | 0 | 1 | 0 | CLOSED
1765 | 1794 | 10 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 9 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000174 | UPVC ball valve 2" PN10 commer | Each | 315.4912 | 1 | Immediate | 315.4912 |  |  | 2022-07-29 | 44.1688 |  | 1 | 1 | 0 | 1 | 0 | CLOSED
1765 | 1794 | 5 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 4 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000168 | UPVC elbow 90 dg -3"PN10 commer | Each | 60.6492 | 6 | Immediate | 363.8953 |  |  | 2022-07-29 | 50.9454 |  | 6 | 6 | 0 | 6 | 0 | CLOSED
1765 | 1794 | 7 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 6 | 1 | 2022-08-06 | 2022-08-11 |  | P060019000170 | UPVC male adaptor 2" PN 10 commer | Each | 20.0877 | 4 | Immediate | 80.3509 |  |  | 2022-07-29 | 11.2492 |  | 4 | 4 | 0 | 4 | 0 | CLOSED
1766 | 1735 | 17 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-06 | 2022-08-11 | /PLAYA Resorts Project | P030030100514 | Bi-Metal Terminal Lugs 16 mm | Each | 3.5 | 50 | Immediate | 175 |  |  | 2022-06-28 | 24.5 |  | 50 | 50 | 0 | 50 | 0 | CLOSED
1766 | 1735 | 13 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 4 | 1 | 2022-08-06 | 2022-08-11 | /PLAYA Resorts Project | P030030100515 | Earth Rod (1.5 Meter ) With Coupling , bolts | Each | 165 | 30 | Immediate | 4950 |  |  | 2022-06-28 | 693 |  | 30 | 30 | 0 | 30 | 0 | CLOSED
1766 | 1735 | 11 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 3 | 1 | 2022-08-06 | 2022-08-11 | /PLAYA Resorts Project | P039010000002 | فيشة نتاية 220 فولت | Each | 10 | 50 | Immediate | 500 |  |  | 2022-06-28 | 70 |  | 50 | 50 | 0 | 50 | 0 | CLOSED
1766 | 1735 | 15 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 5 | 1 | 2022-08-06 | 2022-08-11 | /PLAYA Resorts Project | P030030100522 | Clamps For Earth Rod , Or thermo weld connection | Each | 30 | 30 | Immediate | 900 |  |  | 2022-06-28 | 126 |  | 30 | 30 | 0 | 30 | 0 | CLOSED
1766 | 1735 | 9 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-06 | 2022-08-11 | /PLAYA Resorts Project | P039010000001 | فيشة دكر 220 فولت | Each | 10 | 50 | Immediate | 500 |  |  | 2022-06-28 | 70 |  | 50 | 50 | 0 | 50 | 0 | CLOSED
1766 | 1769 | 3 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 6 | 1 | 2022-08-06 | 2022-08-11 | /PLAYA Resorts Project | P039010000003 | بكرة شريط لحام | Each | 8.5 | 200 | Immediate | 1700 |  |  | 2022-07-18 | 238 |  | 200 | 200 | 0 | 200 | 0 | CLOSED
1766 | 1769 | 5 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 7 | 1 | 2022-08-06 | 2022-08-11 | /PLAYA Resorts Project | P800040000258 | TIE Strap - 30CM - pack | Each | 27 | 20 | Immediate | 540 |  |  | 2022-07-18 | 75.6 |  | 20 | 20 | 0 | 20 | 0 | CLOSED
1767 | 1770 | 5 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 2 | 2022-08-06 | 2022-08-11 |  | P170010001030 | Q-FIX لاصق سيراميك | Bag | 105.4 | 40 | Immediate | 4216 |  |  | 2022-07-19 | 590.24 |  | 0 | 40 | 0 | 40 | 0 | OPEN
1767 | 1770 | 4 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-06 | 2022-08-11 |  | P170010001030 | Q-FIX لاصق سيراميك | Bag | 105.4 | 80 | Immediate | 8432 |  |  | 2022-07-19 | 1180.48 |  | 0 | 80 | 0 | 80 | 0 | OPEN
1768 | 1751 | 3 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-06 | 2022-08-11 |  | P031030000282 | Q-plug- 1 pag = 20 KG | Bag | 394.73 | 4 | Immediate | 1578.92 |  |  | 2022-07-06 | 221.0488 |  | 0 | 4 | 0 | 4 | 0 | OPEN
1769 | 1777 | 3 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-07 | 2022-08-11 |  | P700010000044 | مكنسة بلدية | Each | 45 | 20 | Immediate | 900 |  |  | 2022-07-20 | 126 |  | 20 | 20 | 0 | 20 | 0 | CLOSED
1769 | 1777 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-07 | 2022-08-11 |  | P200010000026 | برويطة تشوينات | Each | 600 | 5 | Immediate | 3000 |  |  | 2022-07-20 | 420 |  | 5 | 5 | 0 | 5 | 0 | CLOSED
1769 | 1777 | 2 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 3 | 1 | 2022-08-07 | 2022-08-11 |  | P200010000451 | مكنسه ناعمه باليد | Each | 25 | 20 | Immediate | 500 |  |  | 2022-07-20 | 70 |  | 20 | 20 | 0 | 20 | 0 | CLOSED
1770 | 1780 | 2 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-07 | 2022-08-11 |  | P060019000101 | طقم جلبة تطويل 2\1" | Each | 35 | 30 | Immediate | 1050 |  |  | 2022-07-21 | 147 |  | 30 | 30 | 0 | 30 | 0 | CLOSED
1771 | 1766 | 4 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 3 | 1 | 2022-08-07 | 2022-08-11 |  | P200010000105 | شريط قياس 5م | Each | 35 | 8 | Immediate | 280 |  |  | 2022-07-17 | 39.2 |  | 8 | 8 | 0 | 8 | 0 | CLOSED
1771 | 1766 | 2 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-07 | 2022-08-11 |  | P200010000918 | قلم ماركر احمر | Each | 20 | 120 | Immediate | 2400 |  |  | 2022-07-17 | 336 |  | 120 | 120 | 0 | 120 | 0 | CLOSED
1771 | 1766 | 3 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-07 | 2022-08-11 |  | P200010001522 | اسبراي الوان | Each | 25 | 10 | Immediate | 250 |  |  | 2022-07-17 | 35 |  | 10 | 10 | 0 | 10 | 0 | CLOSED
1771 | 1766 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 4 | 1 | 2022-08-07 | 2022-08-11 |  | P910010000091 | قلم ماركر يوكن ازرق | Each | 20 | 120 | Immediate | 2400 |  |  | 2022-07-17 | 336 |  | 120 | 120 | 0 | 120 | 0 | CLOSED
1772 | 1771 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-07 | 2022-08-11 |  | P910010000229 | دفتر Material Receiving Voucher | Each | 25 | 100 | Immediate | 2500 |  |  | 2022-07-19 | 0 |  | 100 | 100 | 0 | 100 | 0 | CLOSED
1772 | 1771 | 2 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-07 | 2022-08-11 |  | P910010000386 | دفتر تصريح خروج | Each | 25 | 100 | Immediate | 2500 |  |  | 2022-07-19 | 0 |  | 100 | 100 | 0 | 100 | 0 | CLOSED
1773 | 1793 | 3 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-07 | 2022-08-11 |  | P200010000161 | فيشر 6 مم | Carton | 10 | 16 | Immediate | 160 |  |  | 2022-07-28 | 0 |  | 16 | 16 | 0 | 16 | 0 | CLOSED
1773 | 1793 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-07 | 2022-08-11 |  | P200020000061 | مسمار بورمه 6 مم | Kilogram | 65 | 10 | Immediate | 650 |  |  | 2022-07-28 | 0 |  | 10 | 10 | 0 | 10 | 0 | CLOSED
1774 | 1799 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-07 | 2022-08-11 |  | P200010000048 | تيب دوكو | Each | 20 | 150 | Immediate | 3000 |  |  | 2022-08-03 | 420 |  | 150 | 150 | 0 | 150 | 0 | CLOSED
1775 | 1792 | 3 | APPROVED | PLAYA Resorts Project |  |  | shitter flex | Playa | Mohamed magdy ahmed abo ellla, Mr. | EGP | 3 | 1 | 2022-08-07 | 2022-08-11 |  | P250010000008 | W3 Italian Wired Motor (20 n 21 Kg - 20 n width 2.66 height 2.6 | Each | 12810.75 | 1 | 100% 15 Day | 12810.75 |  |  | 2022-07-28 | 1793.505 |  | 1 | 1 | 0 | 1 | 0 | CLOSED
1775 | 1792 | 2 | APPROVED | PLAYA Resorts Project |  |  | shitter flex | Playa | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-07 | 2022-08-11 |  | P250010000007 | W2 Italian Wired Motor (20 n) 25 Kg - 20 n width 3.16 height 2.6 | Each | 12810.75 | 1 | 100% 15 Day | 12810.75 |  |  | 2022-07-28 | 1793.505 |  | 1 | 1 | 0 | 1 | 0 | CLOSED
1775 | 1792 | 1 | APPROVED | PLAYA Resorts Project |  |  | shitter flex | Playa | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-07 | 2022-08-11 |  | P250010000006 | W1 Italian Wired Motor (20 n) 25 Kg - 20 n width 3.16 height 2.6 | Each | 12810.75 | 1 | 100% 15 Day | 12810.75 |  |  | 2022-07-28 | 1793.505 |  | 1 | 1 | 0 | 1 | 0 | CLOSED
1775 | 1792 | 4 | APPROVED | PLAYA Resorts Project |  |  | shitter flex | Playa | Mohamed magdy ahmed abo ellla, Mr. | EGP | 4 | 1 | 2022-08-07 | 2022-08-11 |  | P250010000009 | W4 Italian Wired Motor (20 n 16 Kg - 20 n width 3.15 height 1.6 | Each | 12810.75 | 1 | 100% 15 Day | 12810.75 |  |  | 2022-07-28 | 1793.505 |  | 1 | 1 | 0 | 1 | 0 | CLOSED
1776 | 1772 | 6 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-08 | 2022-08-11 |  | P340010000001 | بنزين 80 | Liter | 8.5 | 235.294 | Immediate | 1999.999 |  |  | 2022-07-19 | 0 |  | 235.294 | 235.294 | 0 | 235.294 | 0 | CLOSED
1777 | 1806 | 1 | APPROVED | PLAYA Resorts Project |  |  | العزايزى للتوريدات والمقاولات العامة | Playa | Karim Awad Saied Awad, Mr. | EGP | 1 | 1 | 2022-08-08 | 2022-08-11 |  | P140020000042 | طوب اسمنتي مصمت 6*12*25 | Each | 1.28 | 500000 | 100% 30 Days | 640000 |  |  | 2022-08-08 | 89600 |  | 0 | 0 | 0 | 0 | 500000 | OPEN
1778 | 1726 | 2 | APPROVED | PLAYA Resorts Project |  |  | وان واى للحاسبات والنظم | Playa | Mamdouh Abd-Alrahim Mahmoud Koraiem, Mr. | EGP | 1 | 1 | 2022-08-08 | 2022-08-11 | Planning Engineer:Hassan el kholy | PFA8000500066 | Desktop Dell Optiplex 7090 I7 - Ram 16 GB - M2 :256 G- HD :1TB SATA - Dell monitor 24'' - Dell usb keyboard - Dell usb mouse?? | Each | 20614.03 | 1 | 100% 30 Days | 20614.03 |  |  | 2022-06-28 | 2885.9642 | 2022-08-08 | 0 | 0 | 0 | 0 | 1 | OPEN
1779 | 1742 | 1 | APPROVED | PLAYA Resorts Project |  |  | وان واى للحاسبات والنظم | Playa | Mamdouh Abd-Alrahim Mahmoud Koraiem, Mr. | EGP | 1 | 1 | 2022-08-08 | 2022-08-11 | IT-Dep-Electricity safety for file share server | PFA8000100007 | APC Easy UPS BVX 2200VA, 230V, AVR, IEC Sockets | Each | 6578.94 | 1 | 100% 30 Days | 6578.94 |  |  | 2022-07-04 | 921.0516 | 2022-08-08 | 0 | 0 | 0 | 0 | 1 | OPEN
1780 | 1743 | 1 | APPROVED | PLAYA Resorts Project |  |  | وان واى للحاسبات والنظم | Playa | Mamdouh Abd-Alrahim Mahmoud Koraiem, Mr. | EGP | 1 | 1 | 2022-08-08 | 2022-08-11 | Planning Dep-Electricity safety for primavera server | PFA8000100007 | APC Easy UPS BVX 2200VA, 230V, AVR, IEC Sockets | Each | 6578.94 | 1 | 100% 30 Days | 6578.94 |  |  | 2022-07-04 | 921.0516 | 2022-08-08 | 0 | 0 | 0 | 0 | 1 | OPEN
1781 | 1781 | 5 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-08 | 2022-08-11 |  | P800040000007 | TP link Wireless Usb Adapter 100 Mbps TL -WN722N | Each | 165 | 3 | Immediate | 495 |  |  | 2022-07-21 | 69.3 |  | 0 | 3 | 0 | 3 | 0 | OPEN
1781 | 1781 | 2 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-08 | 2022-08-11 |  | P039010000019 | مشترك كهرباء ثلاثى 5 عين | Each | 85 | 6 | Immediate | 510 |  |  | 2022-07-21 | 0 |  | 0 | 6 | 0 | 6 | 0 | OPEN
1781 | 1781 | 7 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 3 | 1 | 2022-08-08 | 2022-08-11 |  | P800500000016 | USB mouse | Each | 90 | 4 | Immediate | 360 |  |  | 2022-07-21 | 0 |  | 0 | 4 | 0 | 4 | 0 | OPEN
1782 | 1779 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4193 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-09 | 2022-08-11 |  | P140010000016 | white cement | Ton | 3030 | 5 | Immediate | 15150 |  |  | 2022-07-21 | 2121 |  | 0 | 5 | 0 | 5 | 0 | OPEN
1782 | 1779 | 3 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4193 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 3 | 1 | 2022-08-09 | 2022-08-11 |  | P200010000757 | اسطوانه تجليخ خرسانه 7 بوصه | Each | 210 | 20 | Immediate | 4200 |  |  | 2022-07-21 | 588 |  | 0 | 20 | 0 | 20 | 0 | OPEN
1782 | 1779 | 4 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4193 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-09 | 2022-08-11 |  | P200010000753 | اسطوانة تجليخ خرسانه 4.50 بوصة | Each | 95 | 20 | Immediate | 1900 |  |  | 2022-07-21 | 266 |  | 0 | 20 | 0 | 20 | 0 | OPEN
1783 | 1805 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-09 | 2022-08-11 |  | P340010000003 | سولار | Liter | 7.8 | 56000 | Immediate | 436800 |  |  | 2022-08-07 | 0 |  | 0 | 56000 | 0 | 56000 | 0 | OPEN
1784 | 1807 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-09 | 2022-08-11 |  | P340010000001 | بنزين 80 | Liter | 8.5 | 1240 | Immediate | 10540 |  |  | 2022-08-07 | 0 |  | 0 | 1240 | 0 | 1240 | 0 | OPEN
1785 | 1702 | 10 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 3 | 1 | 2022-08-10 | 2022-08-17 |  | P330040000008 | حبل + يد دوره | Each | 17 | 10 | Immediate | 170 |  |  | 2022-06-22 | 0 |  | 0 | 10 | 0 | 10 | 0 | OPEN
1785 | 1702 | 12 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-10 | 2022-08-17 |  | P200010001365 | طقم بوجيهات | Each | 200 | 1 | Immediate | 200 |  |  | 2022-06-22 | 0 |  | 0 | 1 | 0 | 1 | 0 | OPEN
1785 | 1702 | 8 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 4 | 1 | 2022-08-10 | 2022-08-17 |  | P330040000020 | بيبه بوجيه هوندا | Each | 15 | 19 | Immediate | 285 |  |  | 2022-06-22 | 0 |  | 0 | 19 | 0 | 19 | 0 | OPEN
1785 | 1787 | 7 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-10 | 2022-08-17 |  | P330040000250 | سير دكاك (700*13) | Each | 15 | 18 | Immediate | 270 |  |  | 2022-07-25 | 0 |  | 0 | 18 | 0 | 18 | 0 | OPEN
1786 | 1524 | 8 | APPROVED | PLAYA Resorts Project |  |  | المروه للتجارة والتوريدات | PLAYA | Karim Awad Saied Awad, Mr. | EGP | 1 | 1 | 2022-08-11 | 2022-08-17 |  | P140010000015 | اسمنت اسود رتبة 42 | Ton | 1447.368 | 60 | 100% 30 Days | 86842.08 |  |  | 2022-05-09 | 12157.8912 |  | 0 | 60 | 0 | 60 | 0 | OPEN
1787 | 1817 | 1 | APPROVED | PLAYA Resorts Project |  |  | بيومكس | Playa | Karim Awad Saied Awad, Mr. | EGP | 1 | 1 | 2022-08-11 | 2022-08-17 |  | P140020000042 | طوب اسمنتي مصمت 6*12*25 | Each | 1.29 | 250000 | 100% 30 Days | 322500 |  |  | 2022-08-10 | 45150 |  | 0 | 185856 | 0 | 170368 | 79632 | OPEN
1788 | 1781 | 6 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 4 | 1 | 2022-08-15 | 2022-08-17 |  | P800040000007 | TP link Wireless Usb Adapter 100 Mbps TL -WN722N | Each | 170 | 4 | Immediate | 680 |  |  | 2022-07-21 | 95.2 |  | 0 | 4 | 0 | 4 | 0 | OPEN
1788 | 1781 | 8 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 5 | 1 | 2022-08-15 | 2022-08-17 |  | P800500000016 | USB mouse | Each | 100 | 3 | Immediate | 300 |  |  | 2022-07-21 | 0 |  | 0 | 3 | 0 | 3 | 0 | OPEN
1788 | 1781 | 4 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 3 | 1 | 2022-08-15 | 2022-08-17 |  | P800040000090 | Laptop power cable | Each | 20 | 1 | Immediate | 20 |  |  | 2022-07-21 | 0 |  | 0 | 1 | 0 | 1 | 0 | OPEN
1788 | 1813 | 2 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 2 | 1 | 2022-08-15 | 2022-08-17 |  | P800500000016 | USB mouse | Each | 100 | 3 | Immediate | 300 |  |  | 2022-08-09 | 0 |  | 0 | 3 | 0 | 3 | 0 | OPEN
1788 | 1813 | 1 | APPROVED | PLAYA Resorts Project |  |  | Petty Cash | P-4168 | Mohamed magdy ahmed abo ellla, Mr. | EGP | 1 | 1 | 2022-08-15 | 2022-08-17 |  | P039010000019 | مشترك كهرباء ثلاثى 5 عين | Each | 90 | 6 | Immediate | 540 |  |  | 2022-08-09 | 0 |  | 0 | 6 | 0 | 6 | 0 | OPEN
1792 | 1820 | 3 | APPROVED | PLAYA Resorts Project |  |  | يثرب للتوريدات العموميه | Playa | Kareem Ashraf Ali Abo Sarie, Mr. | EGP | 2 | 1 | 2022-08-16 | 2022-08-17 |  | P700020000075 | مخدة فايبر | Each | 35 | 30 | 100% after reciving documents. | 1050 |  |  | 2022-08-14 | 147 |  | 0 | 30 | 0 | 0 | 30 | OPEN
1792 | 1820 | 8 | APPROVED | PLAYA Resorts Project |  |  | يثرب للتوريدات العموميه | Playa | Kareem Ashraf Ali Abo Sarie, Mr. | EGP | 3 | 1 | 2022-08-16 | 2022-08-17 |  | P200010001473 | خرطوم أنبوبة بوتاجاز | Meter | 15 | 50 | 100% after reciving documents. | 750 |  |  | 2022-08-14 | 105 |  | 0 | 50 | 0 | 0 | 50 | OPEN
1792 | 1820 | 2 | APPROVED | PLAYA Resorts Project |  |  | يثرب للتوريدات العموميه | Playa | Kareem Ashraf Ali Abo Sarie, Mr. | EGP | 1 | 1 | 2022-08-16 | 2022-08-17 |  | P700020000006 | مرتبة | Each | 210 | 30 | 100% after reciving documents. | 6300 |  |  | 2022-08-14 | 882 |  | 0 | 30 | 0 | 0 | 30 | OPEN
1793 | 1820 | 4 | APPROVED | PLAYA Resorts Project |  |  | مكتب صن رايز للتوريدات العموميه | Playa | Kareem Ashraf Ali Abo Sarie, Mr. | EGP | 2 | 1 | 2022-08-16 | 2022-08-17 |  | P200010001083 | مروحة حائط | Each | 550 | 12 | 100% after reciving documents. | 6600 |  |  | 2022-08-14 | 924 |  | 0 | 10 | 0 | 0 | 12 | OPEN
1793 | 1820 | 7 | APPROVED | PLAYA Resorts Project |  |  | مكتب صن رايز للتوريدات العموميه | Playa | Kareem Ashraf Ali Abo Sarie, Mr. | EGP | 1 | 1 | 2022-08-16 | 2022-08-17 |  | PFA7000200139 | بوتاجاز مسطح 3 عيون | Each | 470 | 5 | 100% after reciving documents. | 2350 |  |  | 2022-08-14 | 329 |  | 0 | 5 | 0 | 0 | 5 | OPEN
1793 | 1820 | 5 | APPROVED | PLAYA Resorts Project |  |  | مكتب صن رايز للتوريدات العموميه | Playa | Kareem Ashraf Ali Abo Sarie, Mr. | EGP | 3 | 1 | 2022-08-16 | 2022-08-17 |  | PFA7000300013 | ثلاجه 10 قدم | Each | 5500 | 6 | 100% after reciving documents. | 33000 |  |  | 2022-08-14 | 4620 |  | 0 | 6 | 0 | 0 | 6 | OPEN
Print Date : 21-Aug-2022 10:17:27 |  | Page 1 of 1 ¦ Page